## Function List
STT | Mã CN | Tên chức năng | Module | Quy trình | Priority | Complexity | FIT/GAP | Giai đoạn | Analysis - Start | Analysis - End | Analysis - Status | Analysis - Estimate MH | Analysis - PIC | Dev - Start | Dev - End | Dev - Status | Dev - Estimate MH | Dev - PIC | UAT - Start | UAT - End | UAT - Status | UAT - PIC | Risk/Blocker
1 | TMS.FR.01 | Chấm công qua app | TMS | TMS.BP.01 - Chấm công | Must-have | Medium | FIT | 1 | 2026-05-29 | 2026-06-03 | Closed | 8 | SonHN6 | 2026-06-08 | 2026-06-18 | Closed | 16 | PhatTPT3 | 2026-06-28 | 2026-07-03 | Closed | BaoLQ31
2 | TMS.FR.02 | Báo cáo công tháng | TMS | TMS.BP.01 - Chấm công | Must-have | High | GAP | 1 | 2026-06-18 | 2026-06-23 | Closed | 12 | SonHN6 | 2026-06-28 | 2026-07-13 | Closed | 24 | PhatTPT3 | 2026-07-18 | 2026-07-23 | In-progress | BaoLQ31, NhiVN | Client thay đổi req
3 | HRM.FR.05 | Quản lý nhân sự | HRM | HRM.BP.02 - Onboarding | Should-have | Low | FIT | 2 | 2026-07-08 | 2026-07-13 | Closed | 4 | CuongNM129 |  |  | Open
4 | PRM.FR.03 | Đánh giá 360 | PRM | PRM.BP.01 - Performance | Could-have | High | Customization | 2 | 2026-04-19 | 2026-04-29 | Closed | 40 | TungTT83 | 2026-06-28 |  | In-progress | 60 | NhuNHT3+ HaiTD16 |  |  |  |  | Complexity cao, cần refactor
5 | SYS.FR.01 | Cấu hình phân quyền | SYS | SYS.BP.01 - Admin | Should-have | High | FIT | 1 | 2026-07-23 | 2026-08-02 | Assigned | 8 | HaiTD16
6 | ESS.FR.10 | Xin phép nghỉ | ESS | ESS.BP.03 - Leave | Must-have | Medium | FIT | 2 | 2026-06-13 | 2026-07-08 | In-progress | 8 | BaoLQ31 | [9 empty] | Đang chờ TL confirm